## Janeczek
Working Hours
DATE | PHASE | TASK | ESTIMATION | ACTUAL | COMMENT
2014-10-24 | Design | ER-Diagram in MYSQL - Workbench | 1:00 | 0:27 | still ongoing
2014-11-13 | Documentation | Technology Description + Further Approach | 1:00 | 0:30
SUM |  |  | 2:00 | 0:57

## Mair
Working Hours
DATE | PHASE | TASK | ESTIMATION | ACTUAL | COMMENT
2014-10-24 | Design | ER-Diagram in Astah | 1:00 | 0:27 | still ongoing
2014-11-13 | Programming | Create-Script + Inserts | 1:00 | 0:40
2014-11-18 | Programming | Coding Thread | 0:30 | 0:20
SUM |  |  | 2:30 | 1:27

## SUM
Working Hours
| NAME | ESTIMATION | ACTUAL
| Janeczek | 2:00 | 0:57
| Mair | 2:30 | 1:27
| SUM | 4:30 | 2:24